## Sheet1
Dep ID | Activity Name | Details | Dependency 1 | Dependency 2 | Dependency 3 | Dependency 4 | Dependency 5 | Cost to Achieve | Cost Savings
DEP-001 | Inventory application interfaces | Catalog all inbound and outbound interfaces for Application X. | [5 empty] | 12000 | 0
DEP-002 | Map critical business reports | Identify reports, dashboards, and downstream consumers that depend on Application X data. | [5 empty] | 9000 | 0
DEP-003 | Assess data quality risks | Profile source data and document cleansing issues before migration planning. | [5 empty] | 15000 | 0
DEP-004 | Confirm compliance requirements | Validate retention, audit, privacy, and regulatory requirements for the migration. | [5 empty] | 8000 | 0
DEP-005 | Define target access model | Design Application Y roles and permission groups for migrated users. | [5 empty] | 10000 | 0
DEP-006 | Prepare vendor support plan | Confirm vendor contacts, escalation paths, and support windows for cutover. | [5 empty] | 6000 | 0
DEP-007 | Baseline current operating costs | Capture current licensing, infrastructure, support, and operational spend for Application X. | [5 empty] | 7000 | 0
DEP-008 | Document integration ownership | Assign accountable owners for each integration and operational handoff. | [5 empty] | 5000 | 0
DEP-009 | Validate security review scope | Confirm security controls, testing scope, and approval checkpoints. | [5 empty] | 11000 | 0
DEP-010 | Create cutover communication plan | Draft stakeholder messaging, readiness updates, and support communications. | [5 empty] | 6500 | 0
DEP-011 | Build migration staging environment | Provision staging resources and connectivity for migration testing. | DEP-001 | DEP-003 |  |  |  | 42000 | 0
DEP-012 | Configure Application Y roles | Implement target roles and groups based on the approved access model. | DEP-005 | DEP-009 |  |  |  | 18000 | 0
DEP-013 | Develop data transformation rules | Create repeatable mappings from Application X data structures to Application Y. | DEP-002 | DEP-003 |  |  |  | 26000 | 0
DEP-014 | Migrate historical transaction data | Load validated historical records into Application Y staging. | DEP-001 | DEP-003 |  |  |  | 58000 | 0
DEP-015 | Connect priority integrations | Repoint high-priority integrations and validate message flow. | DEP-001 | DEP-008 |  |  |  | 37000 | 0
DEP-016 | Run user acceptance testing | Coordinate UAT cycles and resolve issues before production readiness. | DEP-005 | DEP-010 |  |  |  | 22000 | 0
DEP-017 | Prepare operational runbooks | Write support procedures, recovery steps, and ownership details. | DEP-006 | DEP-008 |  |  |  | 9000 | 0
DEP-018 | Execute security validation tests | Complete control validation and document approvals. | DEP-004 | DEP-009 |  |  |  | 16000 | 0
DEP-019 | Train support and power users | Train support teams and departmental power users on Application Y workflows. | DEP-005 | DEP-010 |  |  |  | 13000 | 0
DEP-020 | Finalize production cutover checklist | Confirm readiness criteria, rollback plan, and go/no-go checklist. | DEP-006 | DEP-010 |  |  |  | 7500 | 0
DEP-021 | Switch production users to Application Y | Move users to Application Y and monitor the first production business cycle. | DEP-016 | DEP-019 | DEP-020 |  |  | 14000 | 35000
DEP-022 | Archive Application X records | Archive retained records according to compliance and business requirements. | DEP-014 | DEP-018 |  |  |  | 12000 | 18000
DEP-023 | Disable legacy write access | Lock Application X writes after production cutover to prevent split-brain updates. | DEP-016 | DEP-020 |  |  |  | 4000 | 12000
DEP-024 | Retire duplicate reporting feeds | Remove old reporting feeds after equivalent Application Y reports are validated. | DEP-013 | DEP-015 |  |  |  | 6000 | 42000
DEP-025 | Terminate unused vendor licenses | Cancel unused Application X licenses and support subscriptions. | DEP-012 | DEP-020 |  |  |  | 3000 | 95000
DEP-026 | Decommission legacy integration jobs | Stop scheduled jobs and remove obsolete integration credentials. | DEP-015 | DEP-017 |  |  |  | 8000 | 30000
DEP-027 | Shut down Application X infrastructure | Deprovision servers, databases, storage, and monitoring resources. | DEP-011 | DEP-017 |  |  |  | 10000 | 80000
DEP-028 | Update disaster recovery procedures | Update continuity plans so recovery procedures reference Application Y. | DEP-017 | DEP-020 |  |  |  | 5000 | 10000
DEP-029 | Close audit evidence package | Collect approvals, test results, and operational evidence for audit closure. | DEP-018 | DEP-020 |  |  |  | 7000 | 5000
DEP-030 | Publish benefits realization report | Summarize final costs, savings, risks retired, and follow-up actions. | DEP-013 | DEP-019 |  |  |  | 4500 | 25000